## Sprint 1
Sprint 1 Backlog |  |  | Sprint 1 (1 Week)
Product Backlog Item ID | User Stories (Features) | Initial Estimate (Points) | Day 1 (Hours) | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Assignee
1.1 | As a partner I should be able to submit description of project/task | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | George
1.2 | As an admin I should be able to access the description posted by the partner | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | George
1.3 | As a partner I should be able to choose categories and enter extra attributes for each category | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | George
2.1 | As an admin I should be able to accept and schedule a meeting / decline concerning the posted project | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Mayar
2.2 | As a partner I should be able to accept to arrange a meeting / cancel project | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Khaled
2.3 | As a partner I should be able to define project required skills with a set of attributes (Time, skills, etc…..) | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Khaled
2.4 | As a partner I should be able to choose to have a consultant or not | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Mayar
2.5 | As a partner I should be able to provide detailed description in case of no consulatancy | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Mayar
3.1 | As a choosen consultant I should be able to accept the project by submitting a detailed plan or reject | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Haidy
3.2 | As a partner I should be able to choose a specific consultant or have it assigned randomly | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Haidy
3.3 | As a partner I should be able to accept schdeule negotitation meeting /decline consultant's plan | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Haidy
3.4 | As a consultatnt I should be able to accept meeting arrangement or withdraw from the project | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Yahia
4.1 | As a candidate I should be able to view and search all posted tasks and view recommended tasks | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Yahia
4.2 | As a candidate I should be able to apply for tasks that I am eligible and certified for | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Yahia
4.3 | As an admin I should be able to choose the freelancer that would be assigned | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Yahia
4.4 | As an accepted candidate I should be able to get a notification and an orientation for the task | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Farida
5.1 | As a freelancer I should be able to submit my project | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Dareen
5.2 | As a consulant I should be able to confirm or propose edits for the freelancer's work | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Farida
5.3 | As a contributor I should be able to view the project progress bar | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | farida
5.4 | As a partner I should be able to confirm or propose edit on project's updates | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Tieby
6.1 | As a user I should be able to Register/login/logout/deactivate/delete/edit my account | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Shazly
6.2 | As a user I should be able to choose profile type while registering | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Tieby
6.3 | As a user I should be notified by location and time to sign contract | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Tieby
6.4 | As a user I should be able to show my notifcations | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Tieby
6.5 | As a user I should be able to to show my profile | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Dareen
6.6 | As a user i should see the signed contracnt and the validity of the membership | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Dareen
6.7 | As a consultancy agency I could view basic information/board members/partners/evetns by agency/reports &studies | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Dareen
6.8 | As a partner I should be able to view basic information/board members/partners/evetns by agency/field of work | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fatima
6.9 | As a partner I should be able to view past projects/suggest feedback | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Fatima
6.1 | As a user I should be able to to show my attended events | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Fatima
6.11 | As a user I should be able to to show my completed projects and reviews received and by whom | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Fatima
6.12 | As a user I should be able to to show my certficates and masterclasses | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Claudia
7.1 | As a member I should be able to book an appointment | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Claudia
7.2 | As a member I should be able to view life coach available slots | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Claudia
7.3 | As a life coach I shold be able to view updated schedule | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Shazly
7.4 | As a life coach I should be able to receive a notification about slot reservation in order to decline/accept | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | George
7.5 | As a life coach or member I should be accept/decline/suggest a meeting location | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Dareen
7.6 | As a member and a life coach I should receive a confiramtion notifcation about the meeting | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Farida
7.7 | As a life coach I should be able to post my weekly schedule | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | shazly
| Total Effort | 99 | 62 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Burndown Chart
Note on C2: Initial numeric estimate (size) concluded during Sprint Review

## Sprint 2
Sprint 2 Backlog |  |  | Sprint 2
Product Backlog Item ID | User Stories (Features) | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
| Total Effort | 90 | 87 | 84 | 87 | 75 | 87 | 72 | 72 | 66 | 63 | 43 | 40 | 54 | 51 | 55 | 40 | 35 | 24 | 18 | 9 | 0
Sprint Burndown Chart
Note on C2: Initial numeric estimate (size) concluded during Sprint Review

## Sprint 3
Sprint 3 Backlog |  |  | Sprint 3
Product Backlog Item ID | User Stories (Features) | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
| Total Effort | 90 | 87 | 84 | 87 | 75 | 75 | 72 | 72 | 66 | 63 | 43 | 40 | 54 | 51 | 43 | 35 | 22 | 26 | 15 | 10 | 5
Sprint Burndown Chart
Note on C2: Initial numeric estimate (size) concluded during Sprint Review