## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
7.1 | As a member I should be able to book an appointment | 4 | farida | Ahmed yehia | Mohamed teiby
7.2 | As a member I should be able to view life coach available slots | 2 | Ahmed Elshazly | khaled ahmed | georges khalil
7.3 | As a life coach I shold be able to view updated schedule | 2 | Mohamed teiby | haidy hany | farida
7.4 | As a life coach I should be able to receive a notification about slot reservation in order to decline/accept | 6 | khaled ahmed | claudia | fatma
7.5 | As a life coach or member I should be accept/decline/suggest a meeting location | 5 | georges khalil | mayar | dareen
7.6 | As a member and a life coach I should receive a confiramtion notifcation about the meeting | 5 | haidy hany | Ahmed Elshazly | Ahmed yehia
7.7 | As a life coach I should be able to post my weekly schedule | 7 | Ahmed yehia | Mohamed teiby | khaled ahmed
1.1 | As a partner I should be able to submit description of project/task | 4 | claudia | haidy hany | farida
1.2 | As an admin I should be able to access the description posted by the partner | 3 | fatma | claudia | mayar
1.3 | As a partner I should be able to choose a category for my project | 4 | mayar | fatma | dareen
1.4 | As a partner I should be able to enter extra attributes after I choose category | 5 | dareen | Ahmed Elshazly | Ahmed yehia
5.1 | As a consulant I should be able to confirm or propose edits for the freelancer's work | 5 | farida | Ahmed yehia | Mohamed teiby
5.2 | As a partner/conultant/Member enrolled in project I should be able to view the project current status | 4 | Ahmed Elshazly | khaled ahmed | georges khalil
5.3 | As a partner I should be able to confirm or propose edit on project's updates | 5 | Mohamed teiby | haidy hany | farida
4.1 | As a candidate I should be able to view and search all posted tasks and view recommended tasks | 3 | khaled ahmed | claudia | fatma
4.2 | As a candidate I should be able to apply for tasks that I have the required skills and certified for | 6 | georges khalil | mayar | dareen
4.3 | As an admin I should be able to choose the freelancer that would be assigned | 4 | haidy hany | Ahmed Elshazly | Ahmed yehia
4.4 | As an accepted candidate I should be able to get a notification and an orientation for the task | 4 | Ahmed yehia | Mohamed teiby | khaled ahmed
3.1 | As a choosen consultant I should be able to apply for project by submitting a detailed plan or reject | 3 | claudia | haidy hany | farida
3.2 | As a partner I should be able to choose a specific consultant or have it assigned randomly | 3 | fatma | claudia | mayar
3.3 | As a partner I should be able to accept schdeule negotitation meeting /decline consultant's plan | 4 | mayar | fatma | dareen
3.4 | As a consultatnt I should be able to accept meeting arrangement or withdraw from the project | 4 | dareen | Ahmed Elshazly | Ahmed yehia
Team velocity in Sprint 1= 99/ 3 days= 33 Story Point/day
Team velocity in Sprint 2=83/2 days= 41.5 Story Point/day
Speed up ratio= 41.5/33= 1.26
Team velocity in Sprint 4= 40/4 days= 10 story point/ day
Estimate Team velocity of Sprint 5= 10* .26= 12.6 story point/day