## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Task submission
1.1 | As a partner I should be able to submit description of project/task | 2 | George | NA
1.2 | As an admin I should be able to access the description posted by the partner | 1 | George | NA
1.3 | As a partner I should be able to choose categories and enter extra attributes for each category | 5 | George | NA
2 | Task negotiation
2.1 | As an admin I should be able to accept and schedule a meeting / decline concerning the posted project | 3 | Mayar | 1.1 | as a partner I should submit description and schedule a meeting
2.2 | As a partner I should be able to accept to arrange a meeting / cancel project | 4 | Khaled | 2.1 | as a partner I should schedule a meeting and whether be decliend or accepted
2.3 | As a partner I should be able to define project required skills with a set of attributes (Time, skills, etc…..) | 4 | Khaled | NA
2.4 | As a partner I should be able to choose to have a consultant or not | 2 | Mayar | NA
2.5 | As a partner I should be able to provide detailed description in case of no consulatancy | 3 | Mayar | 2.4 | as a partner I should choose to have a consulatnt or not and in case of no provide detailed description
3 | Consultant assignment
3.1 | As a choosen consultant I should be able to accept the project by submitting a detailed plan or reject | 2 | Haidy | NA
3.2 | As a partner I should be able to choose a specific consultant or have it assigned randomly | 4 | Haidy | NA
3.3 | As a partner I should be able to accept schdeule negotitation meeting /decline consultant's plan | 3 | Haidy | 3.1 | as a partner I should be able to schedule a meeting when the consultant submits his plan
3.4 | As a consultatnt I should be able to accept meeting arrangement or withdraw from the project | 2 | Yahia | NA
4 | Freenlancer Assignment
4.1 | As a candidate I should be able to view and search all posted tasks and view recommended tasks | 3 | Yahia | NA
4.2 | As a candidate I should be able to apply for tasks that I am eligible and certified for | 2 | Yahia | NA
4.3 | As an admin I should be able to choose the freelancer that would be assigned | 3 | Yahia | NA
4.4 | As an accepted candidate I should be able to get a notification and an orientation for the task | 4 | Farida | NA
5 | Project Lifecycle
5.1 | As a freelancer I should be able to submit my project | 1 | Dareen | NA
5.2 | As a consulant I should be able to confirm or propose edits for the freelancer's work | 3 | Farida | NA
5.3 | As a contributor I should be able to view the project progress bar | 1 | farida | NA
5.4 | As a partner I should be able to confirm or propose edit on project's updates | 2 | Tieby | NA
6 | Profile
6.1 | As a user I should be able to Register/login/logout/deactivate/delete/edit my account | 6 | Shazly | NA
6.2 | As a user I should be able to choose profile type while registering | 2 | Tieby | 6.1 | as a userI should be able to choose my profile type while regestiring
6.3 | As a user I should be notified by location and time to sign contract | 2 | Tieby | NA
6.4 | As a user I should be able to show my notifcations | 2 | Tieby | NA
6.5 | As a user I should be able to to show my profile | 2 | Dareen | NA
6.6 | As a user i should see the signed contracnt and the validity of the membership | 2 | Dareen | NA
6.7 | As a consultancy agency I could view basic information/board members/partners/evetns by agency/reports &studies | 2 | Dareen | NA
6.8 | As a partner I should be able to view basic information/board members/partners/evetns by agency/field of work | 2 | Fatima | NA
6.9 | As a partner I should be able to view past projects/suggest feedback | 2 | Fatima | NA
6.1 | As a user I should be able to to show my attended events | 2 | Fatima | NA
6.11 | As a user I should be able to to show my completed projects and reviews received and by whom | 2 | Fatima | NA
6.12 | As a user I should be able to to show my certficates and masterclasses | 2 | Claudia | NA
7 | Life Coach reservation
7.1 | As a member I should be able to book an appointment | 4 | Claudia | NA
7.2 | As a member I should be able to view life coach available slots | 2 | Claudia | NA
7.3 | As a life coach I shold be able to view updated schedule | 2 | Shazly | NA
7.4 | As a life coach I should be able to receive a notification about slot reservation in order to decline/accept | 1 | George | NA
7.5 | As a life coach or member I should be accept/decline/suggest a meeting location | 1 | Dareen | NA
7.6 | As a member and a life coach I should receive a confiramtion notifcation about the meeting | 2 | Farida | NA
7.7 | As a life coach I should be able to post my weekly schedule | 5 | shazly | NA