## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Task submission
1.1 | As a partner I should be able to submit description of project/task | 3 | Mayar | Shazly | Georges
1.2 | As an admin I should be able to access the description posted by the partner | 2 | Georges | Shazly | haidy
1.3 | As a partner I should be able to choose categories and enter extra attributes for each category | 6 | Georges | Shazly | haidy
2 | Task negotiation
2.1 | As an admin I should be able to accept and schedule a meeting / decline concerning the posted project | 4 | Claudia | Shazly | Georges
2.2 | As a partner I should be able to accept to arrange a meeting / cancel project | 5 | Mayar | Shazly | Georges
2.3 | As a partner I should be able to define project required skills with a set of attributes (Time, skills, etc…..) | 3 | Claudia | Shazly | Georges
2.4 | As a partner I should be able to choose to have a consultant or not | 2 | Claudia | Shazly | Georges
2.5 | As a partner I should be able to provide detailed description in case of no consulatancy | 3 | Yehia | Shazly | Georges
3 | Consultant assignment
3.1 | As a choosen consultant I should be able to accept the project by submitting a detailed plan or reject | 4 | Yehia | Mayar | haidy
3.2 | As a partner I should be able to choose a specific consultant or have it assigned randomly | 3 | Khaled | Mayar | haidy
3.3 | As a partner I should be able to accept schdeule negotitation meeting /decline consultant's plan | 5 | Khaled | Mayar | haidy
3.4 | As a consultatnt I should be able to accept meeting arrangement or withdraw from the project | 5 | Mohamed teiby | Mayar | haidy
4 | Freenlancer Assignment
4.1 | As a candidate I should be able to view and search all posted tasks and view recommended tasks | 10 | Farida | Mayar | haidy
4.2 | As a candidate I should be able to apply for tasks that I am eligible and certified for | 2 | Mohamed teiby | Mayar | Shazly
4.3 | As an admin I should be able to choose the freelancer that would be assigned | 2 | Mohamed teiby | Mayar | Shazly
4.4 | As an accepted candidate I should be able to get a notification and an orientation for the task | 3 | Mohamed teiby | Mayar | Shazly
5 | Project Lifecycle
5.1 | As a consulant I should be able to confirm or propose edits for the freelancer's work | 4 | Haidy | Shazly | Farida
5.2 | As a contributor I should be able to view the project progress bar | 1 | Farida | Shazly | Georges
5.3 | As a partner I should be able to confirm or propose edit on project's updates | 3 | Haidy | Shazly | Farida
6 | Profile
6.3 | As a user I should be notified by location and time to sign contract | 2 | Dareen | Farida | Shazly
6.4 | As a user I should be able to show my notifcations | 1 | Haidy | Farida | Shazly
6.5 | As a user I should be able to to show my profile | 1 | Dareen | Farida | Shazly
6.6 | As a user i should see the signed contracnt and the validity of the membership | 1 | Dareen | Farida | Shazly
6.7 | As a consultancy agency I could view basic information/board members/partners/evetns by agency/reports &studies | 1 | Dareen | Farida | Mayar
6.8 | As a partner I should be able to view basic information/board members/partners/evetns by agency/field of work | 1 | Dareen | Farida | Mayar
6.9 | As a partner I should be able to view past projects/suggest feedback | 1 | Dareen | Mayar | Shazly
6.1 | As a user I should be able to to show my attended events | 1 | Shazly | haidy | Mayar
6.11 | As a user I should be able to to show my completed projects and reviews received and by whom | 1 | Shazly | haidy | Mayar
6.12 | As a user I should be able to to show my certficates and masterclasses | 1 | Shazly | haidy | Mayar
7 | Life Coach reservation
7.1 | As a member I should be able to book an appointment | 3 | Shazly | haidy | Georges
7.2 | As a member I should be able to view life coach available slots | 1 | Shazly | haidy | Georges
7.3 | As a life coach I shold be able to view updated schedule | 1 | Shazly | haidy | Georges
7.4 | As a life coach I should be able to receive a notification about slot reservation in order to decline/accept | 2 | Yehia | haidy | Georges
7.5 | As a life coach or member I should be accept/decline/suggest a meeting location | 2 | Fatma | Georges | haidy
7.6 | As a member and a life coach I should receive a confiramtion notifcation about the meeting | 1 | Dareen | Georges | haidy
7.7 | As a life coach I should be able to post my weekly schedule | 6 | Fatma | Georges | haidy